## Details
Task ID | Date | Section | Task / Description | Cost | Money In | Money In Method | Vendor / Contractor | Payment Method | Status | Cost Type | Planned Start Date | Planned End Date | Actual End Date | Notes
1 | 19/8/2025 | Site preparation | amakamba | 1200 |  | Cash |  |  | Completed | Material
2 | 19/8/2025 | Site preparation | imisumari | 3000 |  | Cash |  |  | Completed | Material
3 | 19/8/2025 | Security | umuzamu | 2000 |  | Cash |  |  | Completed | Manpower
4 | 19/8/2025 | Transport | ticket | 500 |  | Cash |  |  | Completed | Material
5 | 19/8/2025 | Site preparation | abayedi | 8000 |  | Cash |  |  | Completed | Manpower
6 | 19/8/2025 | Site preparation | abafundi | 25000 |  | Cash |  |  | Completed | Manpower
7 | 20/8/2025 | money | amafaranga |  | 100000 | Mobile Money |  |  | Completed | cash in
8 | 20/8/2025 | Site preparation | amakamba | 800 |  | Cash |  |  | Completed | Material
9 | 20/8/2025 | money | kubikuza | 1500 |  | Cash |  |  | Completed | cash out
10 | 20/8/2025 | Site preparation | abayedi | 15000 |  | Cash |  |  | Completed | Manpower
11 | 20/8/2025 | Site preparation | abafundi | 20000 |  | Cash |  |  | Completed | Manpower
12 | 21/8/2025 | Site preparation | abafundi | 15000 |  | Cash |  |  | Completed | Manpower
13 | 21/8/2025 | Site preparation | abayedi | 30000 |  | Cash |  |  | Completed | Manpower
14 | 21/8/2025 | money | amafaranga |  | 200000 | Mobile Money |  |  | Completed | cash in
15 | 22/8/2025 | Site preparation | ingorofani | 9000 |  | Cash |  |  | Completed | Repairing
16 | 22/8/2025 | Transport | ticket y'ingorofani | 2000 |  | Cash |  |  | Completed | Material
17 | 22/8/205 | Site preparation | umunyururu | 3000 |  | Cash |  |  | Completed | Material
18 | 22/8/2025 | Site preparation | ingufuri | 1500 |  | Cash |  |  | Completed | Material
19 | 22/8/2025 | Site preparation | kubikuza | 2000 |  | Cash |  |  | Completed | cash out
20 | 22/8/2025 | Site preparation | abayedi | 25000 |  | Cash |  |  | Completed | Manpower
21 | 22/8/205 | Site preparation | umufundi | 15000 |  | Cash |  |  | Completed | Manpower
22 | 22/8/2025 | Site preparation | gupatana umucyingo | 150000 | 150000 | Cash |  |  | Completed | Manpower
23 | 23/8/2025 | Site preparation | imbaho | 1000 |  | Cash |  |  | Completed | Material
24 | 23/8/2025 | money | kubikuza | 1500 |  | Cash |  |  | Completed | cash out
25 | 23/8/2025 | Site preparation | abayedi | 35000 |  | Cash |  |  | Completed | Manpower
26 | 23/8/2025 | Site preparation | umufundi | 15000 |  | Cash |  |  | Completed | Manpower
27 | 24/8/2025 | Site preparation | abayedi | 30000 |  | Cash |  |  | Completed | Manpower
28 | 24/8/2025 | Security | umuzamu | 3000 |  | Cash |  |  | Completed | Manpower
29 | 26/8/2025 | Site preparation | imbaho | 7600 |  | Cash |  |  | Completed | Material
30 | 26/8/2025 | Site preparation | ikayii | 3000 |  | Cash |  |  | Completed | Material
31 | 26/8/2025 | money | kubikuza | 1500 |  | Cash |  |  | Completed | cash out
32 | 26/8/2025 | Site preparation | abayedi | 30000 |  | Cash |  |  | Completed | Manpower
33 | 26/2025 | money | amafaranga |  | 100000 | Cash |  |  | Completed | cash in
34 | 26/8/2025 | Site preparation | umufundi | 15000 |  | Cash |  |  | Completed | Manpower
35 | 28/8/2025 | Site preparation | amafaranga |  | 150000 | Cash |  |  | Completed | cash in
36 | 28/8/2025 | Site preparation | gupatana toilet | 22200 |  | Cash |  |  | Completed | Manpower
37 | 28/8/2025 | Site preparation | gupakurura | 6000 |  | Cash |  |  | Completed | Manpower
38 | 28/8/2025 | Site preparation | umuzamu | 3000 |  | Cash |  |  | Completed | Manpower
39 | 28/8/2025 | Site preparation | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
40 | 28/8/2025 | money | kubikuza | 1500 |  | Cash |  |  | Completed | cash out
41 | 29/8/2025 | Foundation | disk | 3500 |  | Cash |  |  | Completed | Material
42 | 29/8/2025 | Foundation | imbaho | 15000 |  | Cash |  |  | Completed | Material
43 | 29/8/2025 | Transport | ticket | 3000 |  | Cash |  |  | Completed | Material
44 | 29/8/2025 | Security | ingufuri | 3000 |  | Cash |  |  | Completed | Material
45 | 29/8/2025 | Foundation | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
46 | 29/8/2025 | Foundation | umufundi | 15000 |  | Cash |  |  | Completed | Manpower
47 | 29/8/2025 | Foundation | abayedi | 20000 |  | Cash |  |  | Completed | Manpower
48 | 29/8/2025 | money | kubikuza | 1500 |  | Cash |  |  | Completed | cash out
49 | 29/8/2025 | Electrical | umuriro | 2000 |  | Cash |  |  | Completed | Material
50 | 29/8/2025 | Transport | Gasore ticket | 30000 |  | Cash |  |  | Completed | Manpower
51 | 26/10/2025 | money | amafaranga |  | 800000 | Bank Transfer |  |  | Completed | cash in
52 | 26/10/2025 | Site preparation | shitingi | 50000 |  | Mobile Money |  |  | Completed | Material
53 | 26/10/2025 | Transport | ticket | 10000 |  | Cash |  |  | Completed | cash out
54 | 26/10/2025 | Structure / Walls | ibyuma | 234000 |  | Mobile Money |  |  | Completed | Material
55 | 26/10/2025 | Structure / Walls | disk | 8000 |  | Cash |  |  | Completed | Material
56 | 26/10/2025 | Transport | ticket | 4000 |  | Cash |  |  | Completed | cash out
57 | 26/10/205 | money | gasore money | 68000 |  | Cash |  |  | Completed | Manpower
58 | 26/10/2025 | Security | umuzamu | 50000 |  | Mobile Money |  |  | Completed | Manpower
59 | 26/10/2025 | Transport | supervisor | 15000 |  | Cash |  |  | Completed | Manpower
60 | 26/10/2025 | Foundation | imbaho | 30000 |  | Cash |  |  | Completed | Material
61 | 26/10/2025 | Transport | ticket | 2000 |  | Cash |  |  | Completed | Material
62 | 28/10/2025 | Structure / Walls | fille | 45000 |  | Cash |  |  | Completed | Material
63 | 28/10/2025 | Structure / Walls | abaferayeri | 122000 |  | Cash |  |  | Completed | Manpower
64 | 28/10/2025 | Structure / Walls | amakamba | 30000 |  | Cash |  |  | Completed | Material
65 | 28/10/2025 | Site preparation | amabati | 20000 |  | Cash |  |  | Completed | Material
66 | 28/10/2025 | Security | itoroshi | 7500 |  | Cash |  |  | Completed | Material
67 | 28/10/2025 | Transport | ticket | 5000 |  | Cash |  |  | Completed | cash out
68 | 28/10/2025 | Site preparation | imbaho | 15000 |  | Cash |  |  | Completed | Manpower
69 | 28/10/2025 | Site preparation | umufundi | 5000 |  | Cash |  |  | Completed | cash out
70 | 28/10/2025 | money | kubikuza | 1500 |  | Cash |  |  | Completed | Manpower
71 | 28/10/2025 | Foundation | umukozi | 3000 |  | Cash |  |  | Completed | Manpower
72 | 28/10/2025 | Foundation | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
73 | 2025-11-12 | money | amafaranga |  | 600000 | Cash |  |  | Completed | cash in
74 | 2025-11-12 | Foundation | abasharpantier | 63000 |  | Cash |  |  | Completed | Manpower
75 | 2025-11-12 | Foundation | abaferayeri | 35000 |  | Cash |  |  | Completed | Manpower
76 | 2025-12-12 | Foundation | imbaho | 100000 |  | Cash |  |  | Completed | Material
77 | 2025-12-12 | Foundation | ticket imbaho | 8000 |  | Cash |  |  | Completed | Material
78 | 2025-12-12 | Foundation | filla pra | 5000 |  | Cash |  |  | Completed | Material
79 | 2025-12-12 | Foundation | gupakurura cement | 10000 |  | Cash |  |  | Completed | Manpower
80 | 2025-12-12 | Foundation | abasharpantier | 60000 |  | Cash |  |  | Completed | Manpower
81 | 2025-12-12 | Foundation | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
82 | 13/12/2025 | Foundation | imbaho | 30000 |  | Cash |  |  | Completed | Material
83 | 13/12/2025 | Foundation | abasharpantier | 60000 |  | Cash |  |  | Completed | Manpower
84 | 13/12/2025 | Foundation | gukodesha vibrator | 15000 |  | Cash |  |  | Completed | Material
85 | 16/12/2025 | Foundation | abayedi | 20000 |  | Cash |  |  | Completed | Manpower
86 | 16/12/2025 | Foundation | abafundi | 20000 |  | Cash |  |  | Completed | Manpower
87 | 16/12/2025 | Foundation | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
88 | 16/12/2025 | Foundation | vidange | 10000 |  | Cash |  |  | Completed | Material
89 | 17/12/2025 | Foundation | abafundi | 90000 |  | Cash |  |  | Completed | Manpower
90 | 17/12/2025 | Foundation | abayedi | 55000 |  | Cash |  |  | Completed | Manpower
91 | 17/12/2025 | Foundation | gukodesha sottezze | 50000 |  | Cash |  |  | Completed | Manpower
92 | 17/12/2025 | Foundation | petroleum | 4000 |  | Cash |  |  | Completed | Material
93 | 17/12/2025 | Foundation | gukoresha imachine | 35000 |  | Cash |  |  | Completed | Manpower
94 | 17/12/2025 | Foundation | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
95 | 17/12/2025 | Foundation | abayedi | 20000 |  | Cash |  |  | Completed | Manpower
96 | 18/12/2025 | Foundation | abafundi | 20000 |  | Cash |  |  | Completed | Manpower
97 | 18/12/2025 | Foundation | abasharpantier | 36000 |  | Cash |  |  | Completed | Manpower
98 | 18/12/2025 | Foundation | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
99 | 18/12/2025 | Foundation | imbaho | 32000 |  | Cash |  |  | Completed | Material
100 | 18/12/2025 | Foundation | umuriro | 15000 |  | Cash |  |  | Completed | Material
101 | 18/12/2025 | Foundation | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
102 | 19/12/2025 | Structure / Walls | umuriro | 5000 |  | Cash |  |  | Completed | Material
103 | 19/12/2025 | Structure / Walls | socket imachine | 1200 |  | Cash |  |  | Completed | Material
104 | 19/12/2025 | Structure / Walls | isolante | 1000 |  | Cash |  |  | Completed | cash out
105 | 19/12/2025 | Structure / Walls | ticket ibyuma | 25000 |  | Cash |  |  | Completed | Material
106 | 19/12/2025 | Structure / Walls | imbaho | 32000 |  | Cash |  |  | Completed | Manpower
107 | 19/12/2025 | Structure / Walls | abaferayeri | 39000 |  | Cash |  |  | Completed | Manpower
108 | 19/12/2025 | Structure / Walls | abasharpantier | 36000 |  | Cash |  |  | Completed | Manpower
109 | 19/12/2025 | Structure / Walls | abayedi | 26000 |  | Cash |  |  | Completed | Manpower
110 | 19/12/225 | Structure / Walls | umufundi | 10000 |  | Cash |  |  | Completed | Manpower
111 | 19/12/25 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
112 | 22/12/2025 | money | amafaranga |  | 1700000 | Mobile Money |  |  | Completed | cash in
113 | 22/12/2025 | Structure / Walls | abasharpantier | 36000 |  | Cash |  |  | Completed | Manpower
114 | 22/12/2025 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
115 | 22/12/2025 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
116 | 23/12/2025 | Structure / Walls | abasharpantier | 22000 |  | Cash |  |  | Completed | Manpower
117 | 23/12/2025 | Structure / Walls | abaferayeri | 39000 |  | Cash |  |  | Completed | Manpower
118 | 23/12/2025 | Structure / Walls | amakamba | 2500 |  | Cash |  |  | Completed | Material
119 | 23/12/2025 | Structure / Walls | imbaho | 161100 |  | Cash |  |  | Completed | Material
120 | 23/12/2025 | Transport | ticket imbaho | 8000 |  | Cash |  |  | Completed | cash out
121 | 23/12/2025 | Structure / Walls | ishashi | 28000 |  | Cash |  |  | Completed | Material
122 | 23/12/2025 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
123 | 24/12/2025 | Structure / Walls | abaferayeri | 39000 |  | Cash |  |  | Completed | Manpower
124 | 24/12/2025 | Structure / Walls | abasharpantier | 72000 |  | Cash |  |  | Completed | Manpower
125 | 24/12/2025 | Structure / Walls | abayedi | 10000 |  | Cash |  |  | Completed | Manpower
126 | 24/12/2025 | Structure / Walls | gutaba munzu | 30000 |  | Cash |  |  | Completed | Manpower
127 | 24/12/2025 | Structure / Walls | imisumari | 10500 |  | Cash |  |  | Completed | Material
128 | 24/12/2025 | Structure / Walls | udusumari duto | 2200 |  | Cash |  |  | Completed | Material
129 | 24/12/2025 | Structure / Walls | ibyuma(8) | 75000 |  | Cash |  |  | Completed | Material
130 | 24/12/2025 | Structure / Walls | imbaho | 297000 |  | Cash |  |  | Completed | Material
131 | 24/12/2025 | Transport | ibyuma(14) | 72000 |  | Cash |  |  | Completed | Material
132 | 24/12/2025 | Structure / Walls | ticket ibyuma | 8000 |  | Cash |  |  | Completed | cash out
133 | 24/12/2025 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
134 | 24/12/2025 | Structure / Walls | muhuza umuriro | 17000 |  | Cash |  |  | Completed | Repairing
135 | 25/12/2025 | Structure / Walls | abasharpantier | 480000 |  | Cash |  |  | Completed | Manpower
136 | 25/12/2025 | Structure / Walls | umufundi | 15000 |  | Cash |  |  | Completed | Manpower
137 | 25/12/2025 | Structure / Walls | abayedi | 50000 |  | Cash |  |  | Completed | Manpower
138 | 25/12/2025 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
139 | 25/12/2025 | Structure / Walls | udusumari duto | 2500 |  | Cash |  |  | Completed | Material
140 | 25/12/2025 | Security | umuzamu | 50000 |  | Cash |  |  | Completed | Manpower
141 | 25/12/2025 | Structure / Walls | abasharpantier | 36000 |  | Cash |  |  | Completed | Manpower
142 | 29/12/2025 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
143 | 29/12/2025 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
144 | 30/12/2025 | Structure / Walls | gukodesha sottezze | 50000 |  | Cash |  |  | Completed | Manpower
145 | 30/12/2025 | Structure / Walls | petroleum | 4000 |  | Cash |  |  | Completed | Material
146 | 30/12/2025 | Structure / Walls | abayedi | 10000 |  | Cash |  |  | Completed | Manpower
147 | 30/12/2025 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
148 | 31/12/2025 | Structure / Walls | abasharpantier | 72000 |  | Cash |  |  | Completed | Manpower
149 | 31/12/2025 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
150 | 31/12/2025 | Transport | ticket imbaho | 10000 |  | Cash |  |  | Completed | cash out
151 | 31/12/2025 | Structure / Walls | imisumari | 152000 |  | Cash |  |  | Completed | Material
152 | 31/12/2025 | Transport | ticket bugesera | 6000 |  | Cash |  |  | Completed | cash out
153 | 31/12/2025 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
154 | 2026-01-01 | Structure / Walls | abasharpantier | 72000 |  | Cash |  |  | Completed | Manpower
155 | 2026-01-01 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
156 | 2026-01-01 | Structure / Walls | disck | 9000 |  | Cash |  |  | Completed | Material
157 | 2026-01-01 | Structure / Walls | umuhoro | 2500 |  | Cash |  |  | Completed | cash out
158 | 2026-01-01 | Transport | transport imbaho | 2000 |  | Cash |  |  | Completed | Manpower
159 | 2026-01-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
160 | 2026-02-01 | money | amafaranga |  | 400000 | Mobile Money |  |  | Completed | cash in
161 | 2026-02-01 | Structure / Walls | abasharpantier | 72000 |  | Cash |  |  | Completed | Manpower
162 | 2026-02-01 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
163 | 2026-02-01 | Structure / Walls | imisumari(10) | 18500 |  | Cash |  |  | Completed | Material
164 | 2026-02-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
165 | 2026-03-01 | Structure / Walls | abasharpantier | 72000 |  | Cash |  |  | Completed | Manpower
166 | 2026-03-01 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
167 | 2026-03-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
168 | 2026-03-01 | Structure / Walls | imbaho | 221000 |  | Cash |  |  | Completed | Material
169 | 2026-05-01 | Structure / Walls | abasharpantier | 72000 |  | Cash |  |  | Completed | Manpower
170 | 2026-05-01 | Structure / Walls | umuyedi | 50000 |  | Cash |  |  | Completed | Manpower
171 | 2026-05-01 | Structure / Walls | umuriro | 10000 |  | Cash |  |  | Completed | Material
172 | 2026-05-01 | Transport | ticket ibyuma | 45000 |  | Cash |  |  | Completed | Manpower
173 | 2026-05-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
174 | 2026-05-01 | Structure / Walls | kubikuza | 45000 |  | Cash |  |  | Completed | cash out
175 | 2026-05-01 | Structure / Walls | gupakurura | 60000 |  | Cash |  |  | Completed | Manpower
176 | 2026-06-01 | Structure / Walls | abaferayeri | 39000 |  | Cash |  |  | Completed | Manpower
177 | 2026-06-01 | Structure / Walls | abasharpantier | 84000 |  | Cash |  |  | Completed | Manpower
178 | 2026-06-01 | Structure / Walls | imisumari | 6600 |  | Cash |  |  | Completed | Material
179 | 2026-06-01 | Structure / Walls | kubikuza | 1500 |  | Cash |  |  | Completed | cash out
180 | 2026-06-01 | Structure / Walls | disck | 4000 |  | Cash |  |  | Completed | Material
181 | 2026-06-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
182 | 2026-06-01 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
183 | 2026-06-01 | Transport | transport imbaho | 8000 |  | Cash |  |  | Completed | Manpower
184 | 2026-06-01 | Security | umuzamu | 7000 |  | Cash |  |  | Completed | cash out
185 | 2026-07-01 | Structure / Walls | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
186 | 2026-07-01 | Structure / Walls | umuyedi | 5000 |  | Cash |  |  | Completed | Manpower
187 | 2026-07-01 | Structure / Walls | imbaho | 100000 |  | Cash |  |  | Completed | Material
188 | 2026-07-01 | Transport | ticket imbaho | 8000 |  | Cash |  |  | Completed | Manpower
189 | 2026-07-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
190 | 2026-07-01 | Transport | ticket ibyuma | 15000 |  | Cash |  |  | Completed | Material
| 2026-08-01 | money | amafaranga |  | 200000 | Mobile Money |  |  | Completed | cash in
191 | 2026-08-01 | Structure / Walls | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
192 | 2026-08-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
193 | 2026-09-01 | Structure / Walls | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
194 | 2026-09-01 | Structure / Walls | abasharpantier | 22000 |  | Cash |  |  | Completed | Manpower
195 | 2026-09-01 | Structure / Walls | injerekani | 3000 |  | Cash |  |  | Completed | Material
196 | 2026-09-01 | Structure / Walls | disck | 4000 |  | Cash |  |  | Completed | Material
197 | 2026-09-01 | Structure / Walls | isolante | 500 |  | Cash |  |  | Completed | Material
198 | 2026-09-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
199 | 2026-10-01 | money | amafaranga |  | 200000 | Cash |  |  | Completed | cash in
200 | 2026-10-01 | Structure / Walls | abasharpantier | 22000 |  | Cash |  |  | Completed | Manpower
201 | 2026-10-01 | Structure / Walls | abaferayeri | 36000 |  | Cash |  |  | Completed | Manpower
202 | 2026-10-01 | Structure / Walls | disck | 8000 |  | Cash |  |  | Completed | Material
203 | 2026-10-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
204 | 2026-12-01 | Structure / Walls | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
205 | 2026-12-01 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
206 | 13/01/2026 | Security | umuzamu | 13000 |  | Cash |  |  | Completed | Manpower
207 | 13/01/2026 | Structure / Walls | kubikuza | 2000 |  | Cash |  |  | Completed | cash out
208 | 13/01/2026 | Structure / Walls | disck | 4000 |  | Cash |  |  | Completed | Material
209 | 13/01/2026 | money | amafaranga |  | 800000 | Mobile Money |  |  | Completed | cash in
210 | 13/01/2026 | Structure / Walls | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
211 | 13/01/2026 | Structure / Walls | abasharpantier | 22000 |  | Cash |  |  | Completed | Manpower
212 | 13/01/2026 | Structure / Walls | gupakurura woold | 30000 |  | Cash |  |  | Completed | Manpower
213 | 13/01/2026 | Transport | transport woold | 70000 |  | Cash |  |  | Completed | Material
214 | 13/01/2026 | Structure / Walls | gravel | 620000 |  | Cash |  |  | Completed | Material
215 | 14/01/2026 | Structure / Walls | abaferayeri | 51000 |  | Cash |  |  | Completed | Manpower
216 | 14/01/2026 | Structure / Walls | umusharpantier | 10000 |  | Cash |  |  | Completed | Manpower
217 | 14/01/2026 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
218 | 15/01/2026 | Structure / Walls | amafaranga |  | 400000 | Cash |  |  | Completed | cash in
219 | 15/01/2026 | Structure / Walls | kumena dalle | 300000 |  | Cash |  |  | Completed | Manpower
220 | 15/01/2026 | Structure / Walls | umuferayeri | 15000 |  | Cash |  |  | Completed | Manpower
221 | 15/01/2026 | Structure / Walls | umusharpantier | 10000 |  | Cash |  |  | Completed | Manpower
222 | 15/01/2026 | Structure / Walls | supervisor | 10000 |  | Cash |  |  | Completed | Manpower
223 | 15/01/2026 | transport | ticket | 15000 |  | Cash |  |  | Completed | Manpower
224
225
226
227
228
229

## Overview
Section | Cost | Status | Cost Type | Cost | Date | Money In | Cost | 0
Land & Permits | 0 | Not Started | Material | 2627200
Foundation | 1026500 | #REF! | Manpower
Structure / Walls | 4928600 | #REF! | Other | 0 | 19/8/2025 |  | 2000 | -2000
Roofing | 0 | Not Started | cash in | 0 | 19/8/2025 |  | 500 | -2500
Doors & Windows | 0 | Not Started | cash out | 124500 | 19/8/2025 |  | 8000 | -10500
Electrical | 2000 | #REF! | Repairing | 26000 | 19/8/2025 |  | 25000 | -35500
Plumbing | 0 | Not Started |  |  | 20/8/2025 | 100000 |  | 64500
Finishes (Interior) | 0 | Not Started |  |  | 20/8/2025 |  | 800 | 63700
Finishes (Exterior) | 0 | Not Started |  |  | 20/8/2025 |  | 1500 | 62200
Landscaping | 0 | Not Started |  |  | 20/8/2025 |  | 15000 | 47200
Contingency | 0 | Not Started |  |  | 20/8/2025 |  | 20000 | 27200
Security | 135500 | #REF! |  |  | 21/8/2025 |  | 15000 | 12200
money | 77000 | #REF! |  |  | 21/8/2025 | 200000 |  | #REF!
Transport | 330500 | #REF! |  |  | 22/8/2025 |  | 9000 | #REF!
withdrwal | 0 | Not Started |  |  | 22/8/2025 |  | 2000 | #REF!
[5 empty] | 22/8/205 |  | 3000 | #REF!
[5 empty] | 22/8/2025 |  | 1500 | #REF!
[5 empty] | 22/8/2025 |  | 2000 | #REF!
[5 empty] | 22/8/2025 |  | 25000 | #REF!
[5 empty] | 22/8/205 |  | 15000 | #REF!
[5 empty] | 22/8/2025 | 150000 | 150000 | #REF!
[5 empty] | 23/8/2025 |  | 1000 | #REF!
[5 empty] | 23/8/2025 |  | 1500 | #REF!
[5 empty] | 23/8/2025 |  | 35000 | #REF!
[5 empty] | 23/8/2025 |  | 15000 | #REF!
[5 empty] | 24/8/2025 |  | 30000 | #REF!
[5 empty] | 24/8/2025 |  | 3000 | #REF!
[5 empty] | 26/8/2025 |  | 7600 | #REF!
[5 empty] | 26/8/2025 |  | 3000 | #REF!
[5 empty] | 26/8/2025 |  | 1500 | #REF!
[5 empty] | 26/8/2025 |  | 30000 | #REF!
[5 empty] | 26/8/2025 |  | 15000 | #REF!
[5 empty] | 28/8/2025 |  | 22200 | #REF!
[5 empty] | 28/8/2025 |  | 6000 | #REF!
[5 empty] | 28/8/2025 |  | 3000 | #REF!
[5 empty] | 28/8/2025 |  | 5000 | #REF!
[5 empty] | 28/8/2025 |  | 1500 | #REF!
[5 empty] | 29/8/2025 |  | 3500 | #REF!
[5 empty] | 29/8/2025 |  | 15000 | #REF!
[5 empty] | 29/8/2025 |  | 3000 | #REF!
[5 empty] | 29/8/2025 |  | 3000 | #REF!
[5 empty] | 29/8/2025 |  | 51000 | #REF!
[5 empty] | 29/8/2025 |  | 15000 | #REF!
[5 empty] | 29/8/2025 |  | 20000 | #REF!
[5 empty] | 29/8/2025 |  | 1500 | #REF!
[5 empty] | 29/8/2025 |  | 2000 | #REF!
[5 empty] | 29/8/2025 |  | 30000 | #REF!
[5 empty] | 26/10/2025 | 800000 |  | #REF!
[5 empty] | 26/10/2025 |  | 50000 | #REF!
[5 empty] | 26/10/2025 |  | 10000 | #REF!
[5 empty] | 26/10/2025 |  | 234000 | #REF!
[5 empty] | 26/10/2025 |  | 8000 | #REF!
[5 empty] | 26/10/2025 |  | 4000 | #REF!
[5 empty] | 26/10/205 |  | 68000 | #REF!
[5 empty] | 26/10/2025 |  | 50000 | #REF!
[5 empty] | 26/10/2025 |  | 15000 | #REF!
[5 empty] | 26/10/2025 |  | 30000 | #REF!
[5 empty] | 26/10/2025 |  | 2000 | #REF!
[5 empty] | 28/10/2025 |  | 45000 | #REF!
[5 empty] | 28/10/2025 |  | 122000 | #REF!
[5 empty] | 28/10/2025 |  | 30000 | #REF!
[5 empty] | 28/10/2025 |  | 20000 | #REF!
[5 empty] | 28/10/2025 |  | 7500 | #REF!
[5 empty] | 28/10/2025 |  | 5000 | #REF!
[5 empty] | 28/10/2025 |  | 15000 | #REF!
[5 empty] | 28/10/2025 |  | 5000 | #REF!
[5 empty] | 28/10/2025 |  | 1500 | #REF!
[5 empty] | 28/10/2025 |  | 3000 | #REF!
[5 empty] | 28/10/2025 |  | 10000 | #REF!
[5 empty] | 2025-11-12 |  | 63000 | #REF!
[5 empty] | 2025-11-12 |  | 35000 | #REF!
[5 empty] | 2025-12-12 |  | 100000 | #REF!
[5 empty] | 2025-12-12 |  | 8000 | #REF!
[5 empty] | 2025-12-12 |  | 5000 | #REF!
[5 empty] | 2025-12-12 |  | 10000 | #REF!
[5 empty] | 2025-12-12 |  | 60000 | #REF!
[5 empty] | 2025-12-12 |  | 5000 | #REF!
[5 empty] | 13/12/2025 |  | 30000 | #REF!
[5 empty] | 13/12/2025 |  | 60000 | #REF!
[5 empty] | 13/12/2025 |  | 15000 | #REF!
[5 empty] | 16/12/2025 |  | 20000 | #REF!
[5 empty] | 16/12/2025 |  | 20000 | #REF!
[5 empty] | 16/12/2025 |  | 10000 | #REF!
[5 empty] | 16/12/2025 |  | 10000 | #REF!
[5 empty] | 17/12/2025 |  | 90000 | #REF!
[5 empty] | 17/12/2025 |  | 55000 | #REF!
[5 empty] | 17/12/2025 |  | 50000 | #REF!
[5 empty] | 17/12/2025 |  | 35000 | #REF!
[5 empty] | 17/12/2025 |  | 10000 | #REF!
[5 empty] | 17/12/2025 |  | 20000 | #REF!
[5 empty] | 18/12/2025 |  | 20000 | #REF!
[5 empty] | 18/12/2025 |  | 36000 | #REF!
[5 empty] | 18/12/2025 |  | 51000 | #REF!
[5 empty] | 18/12/2025 |  | 32000 | #REF!
[5 empty] | 18/12/2025 |  | 15000 | #REF!
[5 empty] | 18/12/2025 |  | 10000 | #REF!
[5 empty] | 19/12/2025 |  | 5000 | #REF!
[5 empty] | 19/12/2025 |  | 1200 | #REF!
[5 empty] | 19/12/2025 |  | 1000 | #REF!
[5 empty] | 19/12/2025 |  | 25000 | #REF!
[5 empty] | 19/12/2025 |  | 32000 | #REF!
[5 empty] | 19/12/2025 |  | 39000 | #REF!
[5 empty] | 19/12/2025 |  | 36000 | #REF!
[5 empty] | 19/12/2025 |  | 26000 | #REF!
[5 empty] | 19/12/225 |  | 10000 | #REF!
[5 empty] | 19/12/25 |  | 10000 | #REF!
[5 empty] | 22/12/2025 | 1700000 |  | #REF!
[5 empty] | 22/12/2025 |  | 36000 | #REF!
[5 empty] | 22/12/2025 |  | 5000 | #REF!
[5 empty] | 22/12/2025 |  | 10000 | #REF!
[5 empty] | 23/12/2025 |  | 22000 | #REF!
[5 empty] | 23/12/2025 |  | 39000 | #REF!
[5 empty] | 23/12/2025 |  | 2500 | #REF!
[5 empty] | 23/12/2025 |  | 161100 | #REF!
[5 empty] | 23/12/2025 |  | 8000 | #REF!
[5 empty] | 23/12/2025 |  | 28000 | #REF!
[5 empty] | 23/12/2025 |  | 10000 | #REF!
[5 empty] | 24/12/2025 |  | 39000 | #REF!
[5 empty] | 24/12/2025 |  | 72000 | #REF!
[5 empty] | 24/12/2025 |  | 10000 | #REF!
[5 empty] | 24/12/2025 |  | 30000 | #REF!
[5 empty] | 24/12/2025 |  | 10500 | #REF!
[5 empty] | 24/12/2025 |  | 2200 | #REF!
[5 empty] | 24/12/2025 |  | 75000 | #REF!
[5 empty] | 24/12/2025 |  | 297000 | #REF!
[5 empty] | 24/12/2025 |  | 72000 | #REF!
[5 empty] | 24/12/2025 |  | 8000 | #REF!
[5 empty] | 24/12/2025 |  | 10000 | #REF!
[5 empty] | 24/12/2025 |  | 17000 | #REF!
[5 empty] | 25/12/2025 |  | 480000 | #REF!
[5 empty] | 25/12/2025 |  | 15000 | #REF!
[5 empty] | 25/12/2025 |  | 50000 | #REF!
[5 empty] | 25/12/2025 |  | 10000 | #REF!
[5 empty] | 25/12/2025 |  | 2500 | #REF!
[5 empty] | 25/12/2025 |  | 50000 | #REF!
[5 empty] | 25/12/2025 |  | 36000 | #REF!
[5 empty] | 29/12/2025 |  | 5000 | #REF!
[5 empty] | 29/12/2025 |  | 10000 | #REF!
[5 empty] | 30/12/2025 |  | 50000 | #REF!
[5 empty] | 30/12/2025 |  | 4000 | #REF!
[5 empty] | 30/12/2025 |  | 10000 | #REF!
[5 empty] | 30/12/2025 |  | 10000 | #REF!
[5 empty] | 31/12/2025 |  | 72000 | #REF!
[5 empty] | 31/12/2025 |  | 5000 | #REF!
[5 empty] | 31/12/2025 |  | 10000 | #REF!
[5 empty] | 31/12/2025 |  | 152000 | #REF!
[5 empty] | 31/12/2025 |  | 6000 | #REF!
[5 empty] | 31/12/2025 |  | 10000 | #REF!
[5 empty] | 2026-01-01 |  | 72000 | #REF!
[5 empty] | 2026-01-01 |  | 5000 | #REF!
[5 empty] | 2026-01-01 |  | 9000 | #REF!
[5 empty] | 2026-01-01 |  | 2500 | #REF!
[5 empty] | 2026-01-01 |  | 2000 | #REF!
[5 empty] | 2026-01-01 |  | 10000 | #REF!
[5 empty] | 2026-02-01 |  | 72000 | #REF!
[5 empty] | 2026-02-01 |  | 5000 | #REF!
[5 empty] | 2026-02-01 |  | 18500 | #REF!
[5 empty] | 2026-02-01 |  | 10000 | #REF!
[5 empty] | 2026-03-01 |  | 72000 | #REF!
[5 empty] | 2026-03-01 |  | 5000 | #REF!
[5 empty] | 2026-03-01 |  | 10000 | #REF!
[5 empty] | 2026-03-01 |  | 221000 | #REF!
[5 empty] | 2026-05-01 |  | 72000 | #REF!
[5 empty] | 2026-05-01 |  | 50000 | #REF!
[5 empty] | 2026-05-01 |  | 10000 | #REF!
[5 empty] | 2026-05-01 |  | 45000 | #REF!
[5 empty] | 2026-05-01 |  | 10000 | #REF!
[5 empty] | 2026-05-01 |  | 45000 | #REF!
[5 empty] | 2026-05-01 |  | 60000 | #REF!
[5 empty] | 2026-06-01 |  | 39000 | #REF!
[5 empty] | 2026-06-01 |  | 84000 | #REF!
[5 empty] | 2026-06-01 |  | 6600 | #REF!
[5 empty] | 2026-06-01 |  | 1500 | #REF!
[5 empty] | 2026-06-01 |  | 4000 | #REF!
[5 empty] | 2026-06-01 |  | 10000 | #REF!
[5 empty] | 2026-06-01 |  | 5000 | #REF!
[5 empty] | 2026-06-01 |  | 8000 | #REF!
[5 empty] | 2026-06-01 |  | 7000 | #REF!
[5 empty] | 2026-07-01 |  | 51000 | #REF!
[5 empty] | 2026-07-01 |  | 5000 | #REF!
[5 empty] | 2026-07-01 |  | 100000 | #REF!
[5 empty] | 2026-07-01 |  | 8000 | #REF!
[5 empty] | 2026-07-01 |  | 10000 | #REF!
[5 empty] | 2026-07-01 |  | 15000 | #REF!
[5 empty] | 2026-08-01 |  | 51000 | #REF!
[5 empty] | 2026-08-01 |  | 10000 | #REF!
[5 empty] | 2026-09-01 |  | 51000 | #REF!
[5 empty] | 2026-09-01 |  | 22000 | #REF!
[5 empty] | 2026-09-01 |  | 3000 | #REF!
[5 empty] | 2026-09-01 |  | 4000 | #REF!
[5 empty] | 2026-09-01 |  | 500 | #REF!
[5 empty] | 2026-09-01 |  | 10000 | #REF!
[5 empty] | 2026-10-01 | 200000 |  | #REF!
[5 empty] | 2026-10-01 |  | 22000 | #REF!
[5 empty] | 2026-10-01 |  | 36000 | #REF!
[5 empty] | 2026-10-01 |  | 8000 | #REF!
[5 empty] | 2026-10-01 |  | 10000 | #REF!
[5 empty] | 2026-12-01 |  | 51000 | #REF!
[5 empty] | 2026-12-01 |  | 10000 | #REF!
[5 empty] | 13/01/2026 |  | 13000 | #REF!
[5 empty] | 13/01/2026 |  | 2000 | #REF!
[5 empty] | 13/01/2026 |  | 4000 | #REF!
[5 empty] | 13/01/2026 | 800000 |  | #REF!
[5 empty] | 13/01/2026 |  | 51000 | #REF!
[5 empty] | 13/01/2026 |  | 22000 | #REF!
[5 empty] | 13/01/2026 |  | 30000 | #REF!
[5 empty] | 13/01/2026 |  | 70000 | #REF!
[5 empty] | 13/01/2026 |  | 620000 | #REF!
[5 empty] | 14/01/2026 |  | 51000 | #REF!
[5 empty] | 14/01/2026 |  | 10000 | #REF!
[5 empty] | 14/01/2026 |  | 10000 | #REF!
[5 empty] | 15/01/2026 | 400000 |  | #REF!
[5 empty] | 15/01/2026 |  | 300000 | #REF!
[5 empty] | 15/01/2026 |  | 15000 | #REF!
[5 empty] | 15/01/2026 |  | 10000 | #REF!
[5 empty] | 15/01/2026 |  | 10000 | #REF!
[5 empty] | 15/01/2026 |  | 15000 | #REF!

## Settings
Section | PaymentMethod | Status | CostType
Site preparation | Cash | Not Started | Material
Land & Permits | Bank Transfer | In Progress | Manpower
Foundation | Mobile Money | Completed | Other
Structure / Walls | Cheque | Delayed | cash in
Roofing |  |  | cash out
Doors & Windows |  |  | Repairing
Electrical
Plumbing
Finishes (Interior)
Finishes (Exterior)
Landscaping
Contingency
Security
money
Transport
withdrwal